## Slide 1
PROJECT PLAN |  |  |  |  |  |  | 
PROJECT NAME | TOTAL TIME |  |  |  | TOTAL BUDGET |  | 
Budget Smart Home | 6 Months (10. Oct. 2021 ~ 3. Jul. 2022) |  |  |  | 3300$ |  | 
SCOPE |  |  |  |  |  |  | 
Up to 6 months of Hardware warranty and repair (After installation) |  |  |  |  |  |  | 
Unlimited software app maintenance |  |  |  |  |  |  | 
Home Design will not be included in Smart Home Installation |  |  |  |  |  |  | 
OBJECTIVES |  | TECHNICAL REQUIRMENTS |  |  | REVIEWS WITH CUSTOMER |  | 
To create a budget home system that is appropriate for all classes, containing: (1) Smart Thermostats. (2) Lightning. (3) Smart Locks. (4) Security System. The vision is to make smart homes the default option for all family homes within the next 20 years. |  | Computer systems need to have the minimum specs and requirements for the software. developers' convenient |  |  | After finalization, a survey will be presented to the customer in order to optimize our services. |  | 
MILESTONES |  | DELIVERABLES |  |  |  |  | 
Main Project Structure |  | Early Phase | Timeline |  | Third Phase | Prototype | 
Technical Plan |  |  |  |  |  |  | 
Prototype Design |  |  | Budget |  |  |  | 
General App Design |  |  |  |  |  |  | 
App Software Development |  | Second Phase | Technical Manual |  | Final Phase | Approved Software App | 
Finalize Software App |  |  |  |  |  |  | 
Final Testing |  |  | User Interface Design |  |  | Final Test Results | 
Project Final Delivery |  |  |  |  |  |  | 
RESOURCES |  |  |  | TIMELINE |  |  | 
RESOURCE |  | CATEGORY |  | ACTIONS |  |  | DATE (Start ~ End)
 |  |  |  | A. Define Teams |  |  | Oct 10th ~ Oct 17th
Software Developers |  | Human Resources |  | B. Circuit Design |  |  | Oct 17th ~ Nov 7th
Designers |  |  |  | C. System Planning |  |  | Nov 7th ~ Nov 28th
Hardware Technicians/Engineers |  |  |  | D. Prototype Development |  |  | Nov 28th ~ Dec 12th
Office space (For software developers) |  | Workspace |  | E. UI Design |  |  | Dec 12th ~ Dec 26th
 |  |  |  | F. Software App Coding |  |  | Dec 26th ~ Jan 23rd
Warehouse (For Hardware technicians) |  |  |  | G. App Prototype |  |  | Jan 23rd ~ Feb 13th
 |  |  |  | H. Site Construction |  |  | Feb 13th ~ Feb 27th
Delivery trucks |  | Vehicles |  | I. Support & Error Handling |  |  | Feb 27th ~ April 24th
 |  |  |  | J. Warranty |  |  | April 24th ~ May 22nd
Computers for office |  | Tools & Machinary |  | K. Tech Support |  |  | May 22nd ~ Jun 26th
 |  |  |  | L. Project Finalizing |  |  | Jun 26th ~ Jul 3rd

## Slide 2
Smart Home
Hardware
Software
Approved Software App
App Maintenance
Main Circuit
Installation & Checkout
Maintenance
Circuit Design
System Planning
Prototype Development
Site Construction
Support & Error Handling
Warranty Repairs
Software App Coding
UI Design
App Prototype
Tech Support

## Slide 3
Description | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
A. Define Teams |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B. Circuit Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C. System Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
D. Prototype Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
E. UI Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
F. Software App Coding |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
G. App Prototype |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
H. Site Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
I. Support & Error Handling |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
J. Warranty |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
K. Tech Support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
L. Project Finalizing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 4
Activities | Ganna | Aliaa | Fatma | Amira | Hadeer
A. Define Teams | A | C | I | I | R
B. Circuit Design | R | I | R | A | C
C. System Planning | I | A | C | R | C
D. Prototype Development | I | C | A | R | R
E. UI Design | A | I | R | I | C
F. Software App Coding | C | R | R | A | I
G. App Prototype | R | A | C | C | I
H. Site Construction | C | I | A | R | R
I. Support & Error Handling | A | R | R | C | I
J. Warranty | R | R | C | I | A
K. Tech Support | C | A | R | R | C
L. Project Finalizing | R | R | I | C | A
R Responsible
A Accountable
C Consulted
I Informed

## Slide 5
0 | A | 1
0 | Define Teams | 
0 | 1 | 1
1 | B | 4
1 | Circuit Design | 
2 | 3 | 5
1 | E | 3
0 | UI Design | 
1 | 2 | 3
4 | C | 7
1 | System Plan | 
5 | 3 | 8
3 | F | 7
0 | Software App Coding | 
3 | 4 | 7
7 | D | 9
1 | Prototype Development | 
8 | 2 | 10
7 | G | 10
0 | App Prototype | 
7 | 3 | 10
10 | H | 12
0 | Site Construction | 
10 | 2 | 12
12 | I | 20
0 | Support & Error Handling | 
12 | 8 | 20
20 | J | 24
1 | Warranty | 
21 | 4 | 25
20 | K | 25
0 | Tech Support | 
20 | 5 | 25
25 | L | 26
0 | Project Finalizing | 
25 | 1 | 26
ES | ID | EF
SL | Description | 
LS | DUR | LF
Per weeks

## Slide 6
0 | A | 1
0 | 5 | 0
0 | 1 | 1
1 | B | 4
1 | 3 | 1
2 | 3 | 5
1 | E | 3
0 | 2 | 0
1 | 2 | 3
4 | C | 7
1 | 2 | 1
5 | 3 | 8
3 | F | 7
0 | 4 | 0
3 | 4 | 7
7 | D | 9
1 | 2 | 1
8 | 2 | 10
7 | G | 10
0 | 2 | 0
7 | 3 | 10
10 | H | 12
0 | 5 | 0
10 | 2 | 12
12 | I | 20
0 | 2 | 0
12 | 8 | 20
20 | J | 24
1 | 2 | 1
21 | 4 | 25
20 | K | 25
0 | 2 | 0
20 | 5 | 25
25 | L | 26
0 | 1 | 0
25 | 1 | 26
ES | ID | EF
SL | RES | SL
LS | DUR | LF
Per weeks

## Slide 7
ID | RES | DUR | SL | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
A | 5 | 1 | 0 | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B | 3 | 3 | 1 |  | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C | 2 | 3 | 1 |  |  |  |  | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
D | 2 | 2 | 1 |  |  |  |  |  |  |  | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
E | 2 | 2 | 0 |  | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
F | 2 | 4 | 0 |  |  |  | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
G | 2 | 3 | 0 |  |  |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
H | 5 | 2 | 0 |  |  |  |  |  |  |  |  |  |  | 5 | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
I | 2 | 8 | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  | 
J | 2 | 4 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 | 2 | 2 | 2 |  |  | 
K | 2 | 5 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 | 2 | 2 | 2 | 2 |  | 
L | 1 | 1 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 | 
Available Resources |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 
Resource Load |  |  |  | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 2 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 2 | 1 | 

## Slide 8
Category | Identical Risk | Response Action
Technical | Some workers can’t do their tasks due to health problems | Provide health support to the workers, or concluding agreements with the company to provide us with reserve workers. Provide maintenance workers and additional alternative devices.
Application | Malfunction of one of the remote control systems of the devices. Difficulty using the application for the client. | Provide multiple options for operating devices through different operating systems.
Final testing | Wrong conduct of the test during only one time. | Do a test several times at certain intervals to ensure the correctness of the while system, and the test is carried out by specialized people.

## Slide 9
ID | Budget ( 000$ ) | DUR | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
A | _ | 1 | _ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B | 3 | 3 |  | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C | 4 | 3 |  |  |  |  | 2 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
D | 1 | 2 |  |  |  |  |  |  |  | 1 | _ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
E | 1 | 2 |  | 1 | _ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
F | 5 | 4 |  |  |  | 2 | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
G | 2 | 3 |  |  |  |  |  |  |  | 1 | 1 | _ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
H | 3 | 2 |  |  |  |  |  |  |  |  |  |  | 2 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
I | 5 | 8 |  |  |  |  |  |  |  |  |  |  |  |  | 1 | 1 | 1 | 1 | 1 | _ | _ | _ |  |  |  |  |  |  | 
J | 6 | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 | 1 | 2 | 1 |  |  | 
K | 2 | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | _ | 1 | _ | _ | 1 |  | 
L | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 | 
Week Total |  |  | _ | 2 | 1 | 3 | 3 | 2 | 2 | 2 | 1 | _ | 2 | 1 | 1 | 1 | 1 | 1 | 1 | _ | _ | _ | 2 | 2 | 2 | 1 | 1 | 1 | 
Cumulative |  |  | _ | 2 | 3 | 6 | 9 | 11 | 13 | 15 | 16 | 16 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 24 | 24 | 24 | 26 | 28 | 30 | 31 | 32 | 33 |